## Sheet1
Project | System/Application | Subject | Description | Type | Test Phase | Test: Test Phase | Test Priority | Test Complexity | Test Name | Step Name (Design Steps) | Description (Design Steps) | Expected (Design Steps)
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 001_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 25892479 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 001_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 25892479 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 001_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 25892479 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 001_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 25892479 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 002_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 8364516 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 002_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 8364516 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 002_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 8364516 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 002_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 8364516 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 003_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 4306287 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 003_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 4306287 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 003_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 4306287 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 003_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 4306287 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 004_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3309436 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 004_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3309436 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 004_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3309436 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 004_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3309436 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 005_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 13839934 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 005_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 13839934 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 005_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 13839934 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 005_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 13839934 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 006_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 12551864 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 006_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 12551864 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 006_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 12551864 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 006_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 12551864 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 007_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 74234994 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 007_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 74234994 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 007_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 74234994 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 007_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 74234994 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 008_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 10376402 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 008_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 10376402 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 008_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 10376402 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 008_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 10376402 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 009_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3046427 na b2c pres shop | 1 | V Sibele jdi na konkretniho zakaznika a pres roletky zaloz objednavku na aktivaci pevneho internetu | Otevre se kosik
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 009_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3046427 na b2c pres shop | 2 | Pri overeni dostupnosti zadej RUIAN/adresu a proklikni se na dostupne fixni sluzby | RUIAN/adresa byla prijata, objevi se strana s dostupnymi technologiemi
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 009_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3046427 na b2c pres shop | 3 | Objednavku nech v tomto stavu aktivni a udelej prtsc dostupnych technologii s rychlostmi | Prtsc vytvoreny, ulozeny
CCCTR-1388 - Zmena SAC | Siebel_CZ | UAT2\Antosova\2025\Converged Connectivity\NonRelease\CCCTR-1388 - Zmena SAC | Segment: B2C Kanal: SHOP Akce: overeni_dostupnosti | Manual | 4-User Acceptance | 4-User Acceptance | 2-Medium | 3-Big | 009_SHOP_B2C_FWA_Proved overeni dostupnosti u fwa s ruian 3046427 na b2c pres shop | 4 | Material odesli na Vojta Suk, ktery provede kontrolu na backendu | Vojta potvrdi OK